## Marketing Plan Data
Project 1 - Plan |  |  |  | STATUS COLOR LEGEND & TOGGLE
Marketing Plan Lists
|  | Not Started | In Progress | Delayed | Complete | Custom 1 | Custom 2
|  | ON | ON | OFF | ON | OFF | OFF
TASK | STATUS | OWNER | ASSIGNED TO | ANTICIPATED START DATE | ANTICIPATED END DATE | ACTUAL START DATE | ACTUAL END DATE
Creating and cleaning DataFrame from TheMuse API | In Progress | Mark | Mark | 2020-06-13 | 2020-06-16 | 2020-06-13
Merging and cleaning 10 csv files from GlassDoor | Complete | Kristin | Kristin | 2020-06-15 | 2020-06-16 | 2020-06-15 | 2020-06-16
Question(salary) 1a-Line plot, 1b-bar plot | Not Started | Katt | Katt | 2020-06-16 | 2020-06-17
Question(levels) 2a-Pie, 2b-Pie | Not Started | Melissa | Melissa | 2020-06-16 | 2020-06-17
Parse TheMuse API for sector | Not Started | Mark | Mark | 2020-06-17 | 2020-06-18
Parse TheMuse API for job skills | Not Started | Mark | Mark | 2020-06-18 | 2020-06-19
Question(companies) 3a-TBD, 3b-TBD | Not Started | Katt | Katt | 2020-06-18 | 2020-06-19
Question(sectors) 4a-TBD | Not Started | Melissa | Melissa | 2020-06-19 | 2020-06-20
Summary Map | Not Started | Kristin | Kristin | 2020-06-19 | 2020-06-20
Question(skills) - optional | Not Started | Katt | Katt | 2020-06-20 | 2020-06-21
Data-Condas

## Data-Condas
Marketing Plan Lists
Marketing Plan Data
NAME | TITLE
Mark
Kristin
Katt
Melissa
Data-Condas